## BurndownChartTemplate
Man hours
Name of team member | w1 | w2 | w3
Jon Snow | 4 | 2 | 4 | 10
Auri | 2 | 3 | 4 | 9
Fela | 5 | 4 | 3 | 12
Hodor | 3 | 4 | 2 | 9
Total man hours per week | 14 | 13 | 13
Total man hours per sprint | 40
|  | Burn down chart |  |  |  |  | no.of weeks | 3
User Story |  | Task | Start | end of w1 | end of w2 | end of w3
Story 1 |  | Task 1.1 | 5 | 5 | 5 | 5
Story 1 |  | Task 1.2 | 2 | 2 | 2 | 2
Story 1 |  | Task 1.3 | 3 | 3 | 3 | 3
Story 2 |  | Task 2.1 | 5 | 5 | 5 | 5
Story 2 |  | Task 2.2 | 3 | 3 | 3 | 3
Story 3 |  | Task 3.1 | 2 | 2 | 2 | 2
Story 3 |  | Task 3.2 | 3 | 3 | 3 | 3
Story 3 |  | Task 3.3 | 4 | 4 | 4 | 4
Story 3 |  | Task 3.4 | 2 | 2 | 2 | 2
Story 4 |  | Task 4.1 | 3 | 3 | 3 | 3
Story 4 |  | Task 4.2 | 2 | 2 | 2 | 2
Story 4 |  | Task 4.3 | 4 | 4 | 4 | 4
Story 4 |  | Task 4.4 | 2 | 2 | 2 | 2
Ideal - Remaining efforts in uninterrupted working hours |  |  | 40 | 26.6667 | 13.3333 | 0 |  |  | Ideal
Actual - Remaining efforts in uninterrupted working hours |  |  | 40 | 40 | 40 | 40 |  |  | Actual
26.6667
8.3333
Note on F13: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered

## ProductBacklog
User Story | Priority | Optional/ Mandatory
I want to keep a record of my Internet speeds at different date times. | 1 | Mandatory
I want to keep a record of my Internet speeds across varying geographical locations | 2 | Mandatory
I want to compare my Wi-Fi speeds with 3G/4G/LTE speeds | 3 | Mandatory
I want to compare different Wi-Fi network speeds | 4 | Mandatory
I want to be able to add comments to my saved observations | 5 | Mandatory
I want to be able to add photos to my saved observations | 6 | Mandatory
I want to see a statistical summary of all my observations | 7 | Mandatory
I want to share my observations with another via Bluetooth | 8 | Mandatory
I want to visualise my Internet speeds on a map | 9 | Mandatory
I want to know the hotspots with the top five speeds | 10 | Mandatory
I want to track my Internet usage across different activities (on foot, in a vehicle, in a bicycle, still etc) | 11 | Optional
I want to see a statistical summary of all users observations | 12 | Optional
I want to compare my speeds with a selected user | 13 | Optional
I want to share my observations with others on my social network | 14 | Optional

## Sprint1
Man hours
Name of team member | w1 | w2 | w3
Cameron | 2 | 0 | 6 | 8
Hassan | 0 | 0 | 0 | 0
James | 0 | 0 | 0 | 0
Tim | 0 | 0 | 6 | 6
Total man hours per week | 2 | 0 | 12
Total man hours per sprint | 14
BurnDown Sprint 1
[5 empty] | Weeks | 3
| User Storys |  |  | Tasks | Start | Week 1 | Week 2 | Week 3
| Story 1: Major Tasks |  |  | Personas | 2 | 0 | 0 | 2
|  |  |  | Wireframe | 4 | 0 | 0 | 4
| Story 2: Burndown/Backlog |  |  | Sprint 1 - Backlog | 1 | 1 | 0 | 0
|  |  |  | Sprint 1 - Burndown | 2 | 2 | 0 | 0
|  |  |  | Sprint 2 - Backlog | 2 | 0 | 0 | 0
Story 3: Optional Tasks
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 11 | 7.3333 | 3.6667 | 0
| Actual - Remaining efforts in uninterrupted working hours |  |  |  | 11 | 8 | 8 | 2

## Sprint2
Man hours
Name of team member | w1 | w2 | w3
Cameron | 8 | 8 | 8 | 24
Hassan | 0 | 8 | 10 | 18
Fuad | 0 | 0 | 20 | 20
Tim | 0 | 6 | 12 | 18
Total man hours per week | 8 | 22 | 50
Total man hours per sprint | 80
BurnDown Sprint 2
[5 empty] | Weeks | 3
User Storys |  |  | Tasks |  | Start | Week 1 | Week 2 | Week 3
Story 1: Major Tasks |  |  | Class Demo |  |  | 0 | 0
|  |  | Priority Task 1 |  | 4 | 0 | 2 | 4
|  |  | Priority Task 2 |  | 8 | 0 | 3 | 3
|  |  | Priority Task 3 |  | 20 | 0 | 0 | 20
|  |  | Priority Task 4 |  |  | 0 | 0
Story 2: Burndown/Backlog |  |  | Sprint 2 - BurnDown |  | 3 | 1 | 1 | 1
|  |  | Sprint 3 - Backlog |  | 3 | 1 | 1 | 1
Ideal - Remaining efforts in uninterrupted working hours |  |  |  |  | 38 | 25.3333 | 12.6667 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  |  |  | 38 | 36 | 29 | 0

## Sprint3
Man hours
Name of team member | w1 | w2 | w3
Cameron | 4 | 6 | 12 | 22
Hassan | 6 | 6 | 6 | 18
James | 6 | 6 | 6 | 18
Tim | 6 | 6 | 32 | 44
Total man hours per week | 22 | 24 | 56
Total man hours per sprint | 102
BurnDown Sprint 1
[5 empty] | Weeks | 3
User Storys |  |  | Tasks |  | Start | Week 1 | Week 2 | Week 3
Story 1: Priority Tasks |  |  | App Demo |  | 10 | 0 | 0 | 10
|  |  | Priority Task 5 |  | 3 | 3 | 0 | 0
|  |  | Priority Task 6 |  | 3 | 3 | 0 | 0
|  |  | Priority Task 7 |  | 8 | 2 | 2 | 4
|  |  | Priority Task 8 |  | 16 | 0 | 4 | 12
|  |  | Priority Task 9 |  | 10 | 0 | 0 | 0
|  |  | Priority Task 10 |  | 8 | 0 | 3 | 5
Story 2: BurnDown/Backlog |  |  | Sprint 3 - BurnDown |  | 2 | 1 | 0 | 1
Story 3: Report |  |  | Justification |  | 2 | 0 | 0 | 2
|  |  | Retrospection |  | 2 | 0 | 0 | 2
Ideal - Remaining efforts in uninterrupted working hours |  |  |  |  | 64 | 42.6667 | 21.3333 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  |  |  | 64 | 55 | 46 | 10